## Backlog
Id | Name | User story | How to test | Importance | Estimate
1 | Text Annotation Interface | As an annotator, I want to highlight and label entities (people, places, objects) in regional language text. | Test if annotators can highlight text, tag entities, and submit annotations successfully. | 1 | 8
2 | Entity Tagging Functionality | As an annotator, I want to tag entities such as people, places, and objects. | Verify if annotators can accurately tag different entities and save them to the database. | 1 | 6
3 | Annotation Data Storage | As an annotator, I want my annotations to be saved to the database for future review. | Check if annotations are saved in the database and can be retrieved. | 1 | 5
4 | Autosave for Annotations | As an annotator, I want the system to autosave my annotations so I don’t lose progress. | Validate that progress is saved automatically after each annotation without needing manual saves. | 2 | 4
5 | Annotation Progress Tracking | As an annotator, I want to see my progress for the dataset I’m annotating. | Verify that the annotator can view a progress bar indicating how much of the dataset has been annotated. | 2 | 3
6 | Dataset Upload (Admins) | As an admin, I want to upload datasets for annotators to work on. | Test if the admin can upload datasets and check if they are stored correctly in the system. | 1 | 5
7 | Dataset Assignment | As an admin, I want to assign datasets to specific annotators. | Check if the admin can assign datasets to annotators, and the assignment reflects in the annotator’s view. | 1 | 6
8 | Dataset Annotation Notification | As an admin, I want annotators to be notified when a new dataset is assigned. | Verify that annotators receive notifications when a new dataset is assigned to them. | 2 | 3
9 | Review Interface (Admins) | As an admin, I want to review annotations submitted by annotators to ensure quality and accuracy. | Validate if admins can view and review submitted annotations in a dedicated interface. | 1 | 7
10 | Accept/Reject Annotations | As an admin, I want to accept or reject annotations made by annotators. | Test if admins can accept/reject annotations and provide feedback to annotators. | 1 | 4
11 | RBAC for Annotators/Admins | As an admin, I want to manage roles and permissions to control who has access to different parts of the system. | Verify if roles are assigned correctly, ensuring annotators can access only their assigned datasets and admins have full control over all functionalities. | 1 | 8
12 | Multilingual Search | As an annotator, I want to search through the text in multiple languages to easily locate sections for annotation. | Test if the search function works for all supported languages and returns accurate results based on text input. | 2 | 6
13 | Feedback to Annotators | As an admin, I want to give feedback to annotators on rejected annotations. | Check if rejected annotations are returned to annotators with feedback, and they can view and address the feedback. | 2 | 5
14 | Annotation Review Comments | As an annotator, I want to view comments from admins on my annotations for clarity and improvement. | Verify if annotators can access and view comments added by admins to their annotations. | 2 | 4
15 | Bulk Dataset Upload (Admins) | As an admin, I want to upload multiple datasets at once to streamline dataset preparation for annotators. | Validate if admins can upload multiple datasets simultaneously and check if they are stored correctly. | 2 | 5
16 | Export Annotations | As an admin, I want to export annotations in different formats (CSV, JSON) for use in other systems. | Verify if the system allows exporting annotations in various formats and ensures correct data formatting. | 3 | 6
17 | Dataset Preprocessing (Admins) | As an admin, I want to preprocess datasets (e.g., splitting large datasets into smaller ones) before assigning them to annotators. | Check if admins can preprocess datasets and if the system reflects these changes in the assignments. | 2 | 5
18 | Custom Annotation Labels | As an annotator, I want to create custom labels for entities in the dataset for more flexible annotations. | Verify if annotators can create and apply custom labels to entities and save them to the database. | 3 | 7
19 | Annotation Audit Logs | As an admin, I want to view audit logs of who modified or deleted annotations for accountability. | Verify if the system logs actions on annotations and if admins can view these logs. | 2 | 4
20 | Annotation Dispute Resolution | As an annotator, I want to dispute rejected annotations and provide explanations for my decisions. | Check if the system allows annotators to dispute admin feedback and if admins can review and respond to disputes. | 3 | 6
21 | Annotation Filtering by Status | As an annotator, I want to filter my annotations based on status (pending, approved, rejected) to manage my work efficiently. | Verify if annotators can filter annotations by status and the system displays the correct results. | 2 | 5
22 | Dataset Progress Summary for Admins | As an admin, I want to view a summary of progress for all annotators working on a dataset. | Check if the system provides a progress summary for each annotator and dataset in a dashboard format. | 2 | 6
23 | Annotation Consistency Check | As an admin, I want the system to perform consistency checks across annotations for similar entities to reduce errors. | Verify if the system flags inconsistent annotations for review and shows a report to the admin. | 3 | 7
24 | Dataset Categorization | As an admin, I want to categorize datasets by topic, language, or region to organize datasets better. | Verify if admins can create categories and assign datasets to them. | 3 | 5
25 | Data Privacy Control | As an admin, I want to set privacy restrictions on sensitive datasets so that only authorized annotators can access them. | Verify if admins can restrict access to datasets and if unauthorized annotators cannot access them. | 1 | 7
26 | Annotation Versioning | As an annotator, I want to see previous versions of my annotations to track changes over time. | Verify if the system stores and retrieves previous versions of annotations for annotators. | 2 | 6
27 | Annotation History for Admins | As an admin, I want to access the history of modifications made to an annotation by annotators for review purposes. | Verify if admins can see the entire history of changes made to annotations. | 2 | 5
28 | AI-Powered Annotation Suggestions | As an annotator, I want AI-based suggestions for possible annotations to speed up the labeling process. | Check if the AI suggestions appear during annotation and if they are accurate and helpful. | 2 | 8
29 | Dataset Annotation Completion Alerts | As an admin, I want to receive alerts when all assigned annotators complete annotations for a dataset. | Verify if the system sends alerts to admins when a dataset reaches 100% completion. | 2 | 4
30 | Real-Time Collaboration | As an annotator, I want to collaborate in real-time with other annotators working on the same dataset for improved accuracy. | Validate if multiple annotators can annotate the same dataset simultaneously and share updates in real-time. | 3 | 8
31 | Annotation Conflict Resolution for Admins | As an admin, I want the system to highlight conflicting annotations for review so I can resolve discrepancies. | Verify if conflicting annotations are flagged and admins can review them side-by-side. | 2 | 6
32 | Dataset Language Detection | As an admin, I want the system to automatically detect the language of a dataset to ensure annotators are assigned the correct datasets. | Validate if the system accurately detects the dataset language and assigns annotators accordingly. | 2 | 4
33 | Annotator Role-Based Training Material | As an annotator, I want access to role-based training material so I can learn how to use the annotation system efficiently. | Verify if annotators can access training material based on their role and if it’s useful. | 3 | 5
34 | Annotation Template System | As an annotator, I want to use predefined annotation templates to streamline repetitive tasks. | Verify if annotators can apply predefined templates and if they are customizable for different datasets. | 2 | 7
35 | Annotation Comment Threading | As an annotator, I want threaded comments on my annotations so I can discuss them with other annotators or admins. | Check if annotators and admins can create threaded comments on annotations and reply in real-time. | 3 | 6
36 | Multi-Dataset Annotation Comparison | As an admin, I want to compare annotations across multiple datasets to identify patterns and discrepancies. | Validate if admins can select multiple datasets and compare annotations using a comparison tool. | 2 | 7
37 | Annotation Deletion | As an annotator, I want to delete annotations that I believe are incorrect or outdated. | Check if annotators can delete their own annotations and if this action is logged for review. | 2 | 5
38 | Comment Notifications | As an annotator, I want to be notified when someone comments on my annotation, so I can respond quickly. | Verify if annotators receive real-time notifications for comments made on their annotations. | 2 | 3
39 | Sentiment Analysis Integration | As an admin, I want to integrate sentiment analysis for specific datasets to analyze emotional tone in text. | Verify if sentiment analysis can be run on specific datasets and if the results are accurate. | 3 | 8
40 | API Access for External Systems | As an admin, I want external systems to access annotations via an API to integrate with other platforms. | Validate if external systems can access annotations through an API and if the correct data is retrieved. | 1 | 8
41 | Annotation Preview | As an annotator, I want to preview my annotations before submitting them for review to catch any errors. | Verify if annotators can preview annotations before submission and make edits if necessary. | 2 | 5
42 | Annotation Highlighting for Admins | As an admin, I want to highlight annotations that need special attention for quicker review. | Check if admins can highlight certain annotations for follow-up or special review. | 3 | 5
43 | Annotation Time Tracking | As an admin, I want to track the time annotators spend on each dataset to measure efficiency. | Validate if the system tracks and logs time spent on each dataset by each annotator. | 2 | 6
44 | Batch Annotation Review | As an admin, I want to review multiple annotations in a batch to streamline the review process. | Verify if admins can review annotations in bulk and provide batch feedback. | 2 | 7
45 | Dataset Archive Functionality | As an admin, I want to archive datasets that are no longer in use but retain them for future reference. | Check if the system allows admins to archive datasets and retrieve them later if needed. | 3 | 4
46 | Dataset Removal | As an admin, I want to remove datasets that are outdated or no longer useful. | Validate if admins can delete datasets and if the system removes them from storage. | 3 | 4
47 | Annotation Search by Tag | As an annotator, I want to search for specific tags in the annotations to find related entities. | Verify if the search function allows filtering annotations by tag and returns relevant results. | 2 | 6
48 | Notification Management (Admins) | As an admin, I want to manage notifications to ensure annotators are informed without spam. | Verify if admins can control notification frequency and content for annotators. | 2 | 5
49 | Annotator Performance Metrics | As an admin, I want to track annotator performance metrics such as accuracy and speed. | Verify if the system logs performance metrics and generates reports for admins. | 2 | 6
50 | Annotation Interface Customization | As an annotator, I want to customize the interface for ease of use, such as font size and layout. | Validate if the annotator can customize the interface settings and save preferences. | 3 | 7
51 | Annotation Quality Scoring | As an admin, I want to score annotations for quality, so I can identify high- and low-quality work. | Verify if the system allows admins to assign quality scores to annotations. | 2 | 6
52 | Dataset Import from External Sources | As an admin, I want to import datasets from external sources such as APIs or file systems. | Validate if the system supports dataset imports from external systems and processes them correctly. | 2 | 7
53 | Annotation Language Switcher | As an annotator, I want to switch between different languages in a dataset seamlessly. | Verify if annotators can switch languages in a dataset without losing annotations. | 2 | 6
54 | Annotation Export Scheduling | As an admin, I want to schedule exports of annotations to run at specific intervals for automation purposes. | Check if admins can schedule automatic exports and verify the timing and data correctness. | 2 | 6
55 | Annotation Heatmap | As an admin, I want to view a heatmap of heavily annotated sections to identify focus areas in datasets. | Validate if the system generates a heatmap of annotation activity. | 3 | 7
56 | User Feedback Loop | As an admin, I want to provide ongoing feedback to annotators as they work to improve quality in real-time. | Verify if admins can give in-progress feedback and if annotators can receive and act on it immediately. | 2 | 5
57 | Annotation Template Sharing | As an annotator, I want to share custom annotation templates with other annotators to standardize work. | Verify if annotators can create and share templates across teams or groups. | 3 | 6
58 | Annotation Completion Prediction | As an admin, I want to predict when annotators will finish their assignments based on current progress. | Verify if the system estimates completion time based on annotation speed and progress. | 2 | 6
59 | Annotation Quality Report Generation | As an admin, I want to generate detailed reports on annotation quality to share with stakeholders. | Validate if admins can generate and export reports that summarize annotation quality metrics. | 3 | 6
60 | Dataset Duplicate Detection | As an admin, I want the system to detect duplicate datasets so I don’t upload the same content multiple times. | Verify if the system flags duplicate datasets and provides admins with options to resolve them. | 2 | 6
61 | Annotator Role Switching | As an admin, I want to switch an annotator’s role temporarily (e.g., from annotator to reviewer) to manage workload. | Check if admins can reassign roles temporarily and if the system reflects this change instantly. | 3 | 5
62 | Annotation Conflict Highlighting | As an annotator, I want the system to highlight potential conflicts between annotations from different users. | Verify if the system flags conflicting annotations for the same entity and alerts annotators. | 2 | 6
63 | Real-Time Chat for Annotators | As an annotator, I want to chat with other annotators in real-time to discuss specific datasets. | Validate if annotators can send and receive messages related to a specific dataset in real-time. | 3 | 7
64 | Dataset Priority Levels | As an admin, I want to assign priority levels to datasets so annotators know which ones to work on first. | Check if admins can assign priority levels and if annotators can filter datasets based on priority. | 2 | 5
65 | Text Preprocessing Suggestions | As an annotator, I want to receive preprocessing suggestions (e.g., tokenization, stop-word removal) to improve annotation accuracy. | Verify if the system suggests preprocessing steps and if annotators can apply them easily. | 2 | 6
66 | AI-Based Annotation Error Detection | As an admin, I want AI to flag potential errors in annotations for review before finalizing them. | Validate if the AI can detect annotation errors and flag them for admin review. | 2 | 8
67 | Dataset Progress Notifications for Annotators | As an annotator, I want to receive notifications when I’ve reached progress milestones in the dataset. | Verify if the system sends notifications when annotators reach progress markers (e.g., 50%, 75%, 100%). | 3 | 5
68 | Annotation Instruction Guides | As an annotator, I want to view detailed guides and best practices for each dataset to annotate correctly. | Validate if annotators can access dataset-specific guides and if they provide useful instructions. | 2 | 4
69 | Comment Sentiment Analysis | As an admin, I want to analyze the sentiment of comments left by annotators to assess team morale or feedback. | Verify if sentiment analysis can be applied to annotation comments and if results are accurate. | 2 | 6
70 | Voice Input for Annotations | As an annotator, I want to use voice commands to annotate text for faster input. | Validate if voice input accurately translates to text annotations and works across languages. | 3 | 7
71 | Dataset Custom Views | As an admin, I want to create custom views of datasets for annotators to focus on specific sections. | Check if admins can create custom views and if annotators see only the sections assigned to them. | 2 | 6
72 | Annotation Cross-Dataset Search | As an annotator, I want to search across multiple datasets simultaneously to find patterns and correlations. | Validate if the search feature allows for cross-dataset searching and if results are accurate. | 3 | 7
73 | Auto-Assign Datasets Based on Performance | As an admin, I want the system to automatically assign datasets to annotators based on their performance and expertise. | Verify if the system dynamically assigns datasets based on annotators' past performance and speed. | 2 | 8
74 | Multilingual Dataset Analytics | As an admin, I want to analyze datasets across multiple languages to compare annotation performance and accuracy. | Validate if the system provides comparative analytics for multilingual datasets. | 3 | 7
75 | Annotation Skill Assessment for New Annotators | As an admin, I want to assess the skills of new annotators through a training dataset before assigning them real tasks. | Validate if the system provides skill assessment datasets and evaluates annotators' performance accurately. | 2 | 7
76 | Auto-Tagging Suggestions | As an annotator, I want the system to suggest tags based on text content to speed up the annotation process. | Verify if the system generates tag suggestions and if annotators can accept or reject them. | 2 | 8
77 | Annotation Consistency Checker | As an admin, I want to check the consistency of annotations across multiple datasets to maintain uniformity. | Validate if the system compares annotations across datasets and flags inconsistencies. | 3 | 7
78 | Performance Leaderboard for Annotators | As an admin, I want to display a leaderboard for annotators based on their accuracy and speed to encourage healthy competition. | Verify if the leaderboard updates in real-time and ranks annotators accurately based on performance metrics. | 3 | 6
79 | Dataset Version Control | As an admin, I want to manage different versions of a dataset and track changes between versions. | Validate if the system supports versioning of datasets and logs the changes accurately. | 3 | 8
80 | Annotator Feedback Review History | As an annotator, I want to view the history of feedback I've received to track my improvements over time. | Check if annotators can access past feedback and if the system tracks improvements or regressions. | 2 | 5
81 | Annotation Dispute Resolution | As an annotator, I want to dispute feedback or rejected annotations through a formal resolution process. | Validate if annotators can submit disputes and if admins can review and resolve them. | 3 | 7
82 | Time Tracking for Annotators | As an admin, I want to track how much time annotators spend on each dataset to optimize workflow. | Verify if the system logs annotator activity and tracks time spent on datasets accurately. | 2 | 6
83 | Annotator Task Completion Reminder | As an annotator, I want to receive reminders about pending annotations when approaching the deadline. | Validate if the system sends reminders to annotators based on task deadlines. | 2 | 5
84 | Annotation Revision History | As an admin, I want to view a detailed revision history of annotations to track changes over time. | Check if the system logs and displays all revisions made to annotations with time stamps. | 2 | 6
85 | Bulk Annotation Editing | As an annotator, I want to edit multiple annotations at once to save time on repetitive tasks. | Verify if the system allows bulk editing of annotations and if changes are applied correctly. | 3 | 7
86 | Annotator Confidence Level Tagging | As an annotator, I want to tag my annotations with confidence levels (e.g., high, medium, low) for admin review. | Validate if annotators can assign confidence levels and if admins can filter annotations based on this. | 3 | 5
87 | Dataset Change Alerts for Annotators | As an annotator, I want to be notified when changes are made to a dataset I’m working on, such as new content or modifications. | Verify if the system alerts annotators when admins update or modify a dataset. | 2 | 5
88 | Annotation Previews Before Submission | As an annotator, I want to preview my annotations before submitting to ensure everything is correct. | Check if the system allows annotators to preview annotations and make adjustments before submission. | 3 | 5
89 | Searchable Feedback Database for Annotators | As an annotator, I want to search through past feedback to learn from other annotators’ experiences. | Validate if annotators can search the feedback database and if results are relevant and accessible. | 2 | 6
90 | Annotation Speed Improvement Suggestions | As an annotator, I want the system to provide suggestions on how to improve my speed and accuracy while annotating. | Verify if the system provides actionable feedback on how to improve speed and efficiency. | 3 | 7
91 | Dataset Annotation Simulation | As an admin, I want to simulate the annotation process on a test dataset to assess system performance. | Validate if the system supports annotation simulation and if it mimics real-world scenarios. | 3 | 7
92 | Annotation Timeout Alerts | As an admin, I want to receive alerts when annotators take too long to complete a dataset or task. | Verify if the system tracks task completion time and sends alerts when tasks exceed the time limit. | 2 | 5
93 | Role-Based Annotation Review | As an admin, I want specific users with review permissions to be able to approve or reject annotations. | Validate if only authorized reviewers can approve or reject annotations. | 2 | 6
94 | AI-Powered Dataset Insights | As an admin, I want AI to analyze datasets and provide insights, such as commonly tagged entities or difficult sections. | Verify if the AI analyzes datasets and generates insights that are useful for annotators and admins. | 2 | 8
95 | Annotator Task Assignment Preferences | As an annotator, I want to set preferences for the types of tasks or datasets I prefer to work on. | Verify if annotators can set task preferences and if the system assigns tasks based on those preferences. | 2 | 5
96 | Offline Annotation Mode | As an annotator, I want to work on annotations offline and sync them when I regain internet access. | Verify if the system allows offline annotations and syncs them accurately when back online. | 3 | 8
97 | Bulk Dataset Import | As an admin, I want to import multiple datasets at once to streamline the dataset preparation process. | Validate if the system supports bulk dataset import and if it handles the import without errors. | 2 | 7
98 | Annotator Task Difficulty Indicator | As an annotator, I want to see the difficulty level of tasks to plan my work accordingly. | Check if the system provides difficulty indicators for each dataset or annotation task. | 2 | 6
99 | Personalized Dashboard for Annotators | As an annotator, I want a personalized dashboard where I can see my assigned tasks, progress, and feedback in one place. | Validate if annotators have access to a dashboard and if it shows all relevant data. | 3 | 6
100 | Annotation Accessibility Features | As an annotator, I want accessibility features, such as screen readers and high-contrast modes, to assist with my work. | Validate if the system supports accessibility features and if they work correctly for annotators with disabilities. | 3 | 6
101 | Download Annotated Dataset | As a researcher, I want to download the annotated dataset in CSV or JSON format, so I can use it in my NLP pipeline. | Test if the dataset can be exported and downloaded in both CSV and JSON formats. Verify the file structure. | 1 | 3
102 | Retrieve Annotation Statistics | As a researcher, I want to retrieve annotation statistics (like frequency of certain tags), so I can understand the dataset’s structure. | Run a query on the dataset to retrieve tag frequencies and verify the accuracy and completeness of the results. | 2 | 4
103 | Keyword Search for Relevant Segments | As an end-user, I want to search for a keyword and see the relevant text segments, so I can gather the information I need. | Test the search functionality by entering a keyword and verifying that all relevant text segments are displayed. | 3 | 1
104 | Suggest Similar Content in Regional Languages | As an end-user, I want the system to suggest similar content in other regional languages, so I can broaden my knowledge base. | Test content suggestion for multiple regional languages and check if similar content is suggested correctly. | 2 | 2

## Features Used in W&P
Id | Name | User story
1 | Text Annotation Interface | As an annotator, I want to highlight and label entities (people, places, objects) in regional language text.
2 | Entity Tagging Functionality | As an annotator, I want to tag entities such as people, places, and objects.
3 | Review Interface (Admins) | As an admin, I want to review annotations submitted by annotators to ensure quality and accuracy.
4 | Accept/Reject Annotations | As an admin, I want to accept or reject annotations made by annotators.
5 | Multilingual Search | As an annotator, I want to search through the text in multiple languages to easily locate sections for annotation.
6 | Multi-Dataset Annotation Comparison | As an admin, I want to compare annotations across multiple datasets to identify patterns and discrepancies.
7 | Dataset Deletion | As an annotator, I want to delete dataset that I believe are incorrect or outdated.
8 | Keyword Search for Relevant Segments | As an end-user, I want to search for a keyword and see the relevant text segments, so I can gather the information I need.
9 | Dataset Upload (Admins) | As an admin, I want to upload datasets for annotators to work on.